## Project Milestone
SMT line | 3A
FATP line | 4A
Package line | 5M
Project | Site | Line | Retrofit timing | Transfer to VN | Line set up & debug | Line qual | FATP Trial run date | FAT Trial run q'ty | Packing trial run | Line qual Approval | SMT OP qual approval | FATP OP qual approval | Shift | PVT SMT | PVT FATP Ramp | FAI report submission | FAI approval | Cut-off data for reports | REL | CET test report submission | Internal PO shipment date | Internal PO-validation result | Submit reports date | OK2ship | FFS | Remark
Calypso | VN | Line 1: POR line SMT * 1 + FATP * 1 + Packing * 1 | / | / | POR line (Use from DVT) | 11/03~11/12 | 2025-11-12 | 60pcs (5 panels) | 12pcs | SMT: 11/12/2025 FATP: 11/12/2025 Packing: 11/15/2025 | 2025-11-13 | 2025-11-15 | DS | 2025-11-14 | 11/17~12/02 | 2025-11-15 | 2025-11-15 | 2025-12-01 | TBD | 2025-12-01 | WK11/16: 1681x (Before OK2S) WK12/07: 940x (after OK2S) | TBD | 2025-12-02 | 2025-12-08 | 2025-12-10 | Ramp up to 95% eficiency until cut off date
[13 empty] | NS |  | 11/18~12/03 | 11/19/2025 9:00am | 11/19/2025 10:00am | [8 empty] | Ramp up to 95% eficiency until cut off date
|  | Line 2: FATP Retrofit from VN Sheldon SMT * 1 + FATP * 1 + Packing * 1 | 09/15~10/18 | 10/20~11/22 (SMT HDMI pressing machine) | SMT: 11/23 Others: 11/07~11/11 | SMT: 11/24 Others: 11/10~11/20 | 2025-11-17 | 60pcs (5 panels) | 12pcs | SMT: 11/24/2025 FATP: 11/17/2025 Packing: 11/20/2025 | 2025-11-24 | 2025-11-19 | DS | 2025-11-25 | 11/20~12/05 | 11/20/2025 1:00pm | 11/20/2025 2:00pm | [8 empty] | Ramp up to 85% eficiency until cut off date
[13 empty] | NS |  | 11/21~12/06 | 11/22/2025 9:00am | 11/22/2025 10:00am | [8 empty] | Ramp up to 80% eficiency until cut off date
|  | Line 3: FATP Retrofit from LH Sheldon. (Auto HSG assembly line retrofit from Callie VN) SMT * 1 + FATP * 1 + Packing * 1 | 09/15~11/08 | 10/20~11/22 (SMT HDMI pressing machine) | SMT: 11/24 Others: 11/10~11/18 | SMT: 11/25 Others: 11/13~11/25 | 2025-11-20 | 60pcs (5 panels) | 12pcs | SMT: 11/25/2025 FATP: 11/20/2025 Packing: 11/25/2025 | 2025-11-25 | 2025-11-22 | DS | 2025-11-26 | 11/24~12/09 | 11/24/2025 1:00pm | 11/24/2025 2:00pm | [8 empty] | Ramp up to 60% eficiency until cut off date
[13 empty] | NS |  | 11/25~12/10 | 11/26/2025 9:00am | 11/26/2025 10:00am | [8 empty] | Ramp up to 50% eficiency until cut off date
|  | Line 4: FATP Retrofit from LH Sheldon. (Auto HSG assembly line retrofit from Callie VN) FATP * 1 + Packing * 2 | 09/15~11/08 | 10/20~11/20 | 11/12~11/21 | 11/17~12/01 | 2025-11-24 | 60pcs (5 panels) | 12pcs/line | FATP: 11/25/2025 Packing: 12/01/2025 | / | 2025-11-26 | DS | / | 11/27~12/12 | 11/27/2025 1:00pm | 11/27/2025 2:00pm | [8 empty] | Ramp up to 30% eficiency until cut off date
[13 empty] | NS |  | 11/28~12/13 | 11/29/2025 9:00am | 11/29/2025 10:00am | [8 empty] | Ramp up to 20% eficiency until cut off date
Plan
On-going
Closed
Summary:
Risk:
SMT S12 & S1 pending HDMI press machine
Auto panel assy Line 4 pending HDMI laser etching machine

## HSG & Auto PKG line mitigation (hidden)
Project | Site | Line | Process | Retrofit FAB timing | Transfer to VN | Line set up & debug | Line qual | FATP Trial run date | Remark
Calypso | VN | Line 1: POR line SMT * 1 + Panel Assembly * 1 + Packing * 1 | Panel Assembly | / | / | POR line (Use from DVT) | 11/03~11/12 | 2025-11-12
Housing Assembly
|  | Line 2: FATP Retrofit from LH Sheldon. SMT * 1 + FATP * 1 + Packing * 1 | Panel Assembly | 09/15~10/18 | 10/20~11/01 | 11/03~11/09 | 11/10~11/15 | 2025-11-17
Housing Assembly
|  | Line 3 * Line 4: Housing 2nd line | Original plan | 09/01~10/18 | 10/20~11/01 | 11/03~11/11 | 11/12~11/19 | 2025-11-20
|  |  | Updated plan | 09/01~11/08 (Delay 3 wks) | 11/10~11/22 | 11/24~12/02 | 12/03~12/10 | 2025-12-11
|  |  | Mitigation plan: Retrofit Callie VN housing line | 10/13~11/08 | / | 11/10~11/13 | 11/14~11/19 | 2025-11-20
|  | Auto Packing line | Original plan | 09/14~11/15 | 11/17~12/01 | 12/02~12/08 | 12/08~12/12 | 12/13/2025
|  |  | Updated plan | 09/14~11/29 (Delay 2 wks) | 12/01~12/15 | 12/16~12/22 | 12/23~12/27 | 2025-12-29
|  |  | Mitigation plan: Qualify Manual Packing 5th line in PVT | / | / | 11/03~11/10 | 11/24~11/25 | 2025-11-26
Summary:
Risk:

## Line qual Milestone
PVT Auto fungible 1.0 line * 4 | [16 empty] | Actual
No | Process | Lines | Items | Start date | End date | Lead time | Status | 2025-09-01 | [27 empty] | 2025-10-01 | [27 empty] | 2025-11-01 | [34 empty] | 2025-12-01
[8 empty] | 2025-09-07 | [6 empty] | 2025-09-14 | [6 empty] | 2025-09-21 | [6 empty] | 2025-09-28 | [6 empty] | 2025-10-05 | [6 empty] | 2025-10-12 | [6 empty] | 2025-10-19 | [6 empty] | 2025-10-26 | [6 empty] | 2025-11-02 | [6 empty] | 2025-11-09 | [6 empty] | 2025-11-16 | [6 empty] | 2025-11-23 | [6 empty] | 2025-11-30 | [6 empty] | 2025-12-07 | [6 empty] | 2025-12-14 | [6 empty] | 2025-12-21 | [6 empty] | 2025-12-28
[8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | SMT | SMT S2 line | Line setup (HDMI press) | 2025-11-07 | 2025-11-08 | 2 | Closed | 2025-11-02 7: Set up
|  |  | Line debug and qualification | 2025-11-10 | 2025-11-11 | 2 | Closed | 2025-11-09 10: Debug
|  |  | Approve | 2025-11-12 | 2025-11-13 | 2 | On-going | 2025-11-09 12: Approve
|  | SMT S12 line | HDMI press machine transfer | 2025-11-05 | TBD |  | stuck at China customs | 2025-11-02 5: Delivery
|  |  | Line setup (HDMI press) | TBD | TBD
|  |  | Line debug and qualification | TBD | TBD
|  |  | Approve | TBD | TBD
|  | SMT S1 line | HDMI press machine transfer | 2025-11-05 | TBD |  | stuck at China customs | 2025-11-02 5: Delivery
|  |  | Line setup (HDMI press) | TBD | TBD
|  |  | Line debug and qualification | TBD | TBD
|  |  | Approve | TBD | TBD
2 | BFT testing | Test Line #1 Auto BFT (Reuse from DVT) L1 start date: 11/17 | Debug | 2025-10-22 | 2025-10-25 | 3 | Closed | 2025-10-19 22: Debug
|  |  | Line qual | 2025-11-03 | 2025-11-10 | 7 | Closed | 2025-11-02 3: Line qual
|  |  | Trial run | 2025-11-12 | 2025-11-12 | 1 | On-going | bar: 2025-11-09 12
|  |  | Approve | 2025-11-12 | 2025-11-13 | 2 | On-going | 2025-11-09 11: Approve
|  | Test Line #2 Auto BFT (Transfer from LH) L2 start date: 11/20 | Transfer from LH | 2025-09-15 | 2025-09-27 | 12 | Closed | 2025-09-14 15: Line transfer from LH
|  |  | Fixture modification | 2025-09-22 | 2025-10-25 | 33 | Closed | 2025-09-21 22: PR,PO; 2025-09-28 29: Fabrication
|  |  | Line setup & Debug | 2025-10-27 | 2025-11-08 | 12 | Closed | 2025-10-26 27: Setup & debug
|  |  | Line qual | 2025-11-10 | 2025-11-14 | 5 | On-going | 2025-11-09 10: Line qual
|  |  | Trial run | 2025-11-17 | 2025-11-17 | 1 | Open | bar: 2025-11-16 17
|  |  | Approve | 2025-11-15 | 2025-11-17 | 2 | Open | 2025-11-09 15: Approve
|  | Test Line #3 Auto BFT L3 start date: 11/24 | Fixture modification | 2025-09-22 | 2025-10-29 | 37 | Closed | 2025-09-21 22: PR,PO; 2025-09-28 29: Fabrication
|  |  | Line setup & Debug | 2025-10-30 | 2025-11-12 | 13 | On-going | 2025-10-26 30: Setup & debug
|  |  | Line qual | 2025-11-13 | 2025-11-18 | 5 | Open | 2025-11-09 13: Line qual
|  |  | Trial run | 2025-11-20 | 2025-11-20 | 1 | Open | bar: 2025-11-16 20
|  |  | Approve | 2025-11-19 | 2025-11-20 | 2 | Open | 2025-11-16 19: Approve
|  | Test Line #4 Auto BFT L4 start date: 11/27 | Fixture modification | 2025-09-22 | 2025-11-01 | 40 | Closed | 2025-09-21 22: PR,PO; 2025-09-28 29: Fabrication
|  |  | Line setup & Debug | 2025-11-03 | 2025-11-12 | 9 | On-going | 2025-11-02 3: Setup & debug
|  |  | Line qual | 2025-11-13 | 2025-11-18 | 5 | Open | 2025-11-09 13: Line qual
|  |  | Trial run | 2025-11-24 | 2025-11-24 | 1 | Open | bar: 2025-11-23 24
|  |  | Approve | 2025-11-19 | 2025-11-20 | 2 | Open | 2025-11-16 19: Approve
3 | HDMI laser etching | Line #1 (DVT line) | Set up | / | / |  | Closed
|  |  | Debug | / | / |  | Closed
|  |  | Trial run | 2025-11-12 | 2025-11-12 | 1 | On-going | bar: 2025-11-09 12
|  |  | Approve | 2025-11-13 | 2025-11-14 | 2 | Open | 2025-11-09 13: Approve
|  | Line #2 (leverage from Callie VN) | Set up | 2025-11-10 | 2025-11-11 | 2 | Closed | 2025-11-09 10: Set up
|  |  | Debug | 2025-11-12 | 2025-11-15 | 4 | On-going | 2025-11-09 12: Debug
|  |  | Trial run | 2025-11-17 | 2025-11-17 | 1 | Open | bar: 2025-11-16 17
|  |  | Approve | 2025-11-17 | 2025-11-18 | 2 | Open | 2025-11-16 17: Approve
|  | Line #3 (leverage from Callie VN) | Set up | 2025-11-11 | 2025-11-12 | 2 | On-going | 2025-11-09 11: Set up
|  |  | Debug | 2025-11-13 | 2025-11-17 | 4 | Open | 2025-11-09 13: Debug
|  |  | Trial run | 2025-11-20 | 2025-11-20 | 1 | Open | bar: 2025-11-16 20
|  |  | Approve | 2025-11-21 | 2025-11-22 | 2 | Open | 2025-11-16 21: Approve
|  | Line #4 (transfer from China) | Line transfer | 2025-11-03 | TBD |  | stuck at China customs | 2025-11-02 3: Delivery
|  |  | Set up | TBD | TBD
|  |  | Debug | TBD | TBD
|  |  | Trial run | 2025-11-24 | 2025-11-24 | bar: 2025-11-23 24
Approve
4 | Auto Panel assembly | ASSY AUTO: Panel Line*1 (DVT line) | Line setup & Debug | 2025-10-27 | 2025-11-01 | 5 | Closed | 2025-10-26 27: Set up
|  |  | Line qual | 2025-11-03 | 2025-11-10 | 7 | Closed | 2025-10-26 1: Line qual
|  |  | Trial run | 2025-11-12 | 2025-11-12 | 1 | On-going | bar: 2025-11-09 12
|  |  | Approve | 2025-11-13 | 2025-11-14 | 2 | On-going | 2025-11-09 11: Approve
|  | ASSY AUTO: Panel Line*2 (retrofit from Sheldon VN) | Line setup & Debug | 2025-11-07 | 2025-11-11 | 4 | Closed | 2025-11-02 7: Set up & debug
|  |  | Line qual | 2025-11-12 | 2025-11-15 | 3 | On-going | 2025-11-09 12: Line qual
|  |  | Trial run | 2025-11-17 | 2025-11-17 | 1 | Open | bar: 2025-11-16 17
|  |  | Approve | 2025-11-17 | 2025-11-18 | 2 | Open | 2025-11-16 17: Approve
|  | ASSY AUTO: Panel Line*3 (transfer from China) Start date: 11/24 | Line transfer | 2025-10-19 | 2025-11-06 | 18 | Closed | 2025-10-19 20: Line transfer from LH
|  |  | Line setup & Debug | 2025-11-10 | 2025-11-14 | 5 | On-going | 2025-11-09 10: Set up & debug
|  |  | Line qual | 2025-11-15 | 2025-11-19 | 4 | Open | 2025-11-09 15: Line qual
|  |  | Trial run | 2025-11-20 | 2025-11-20 | 1 | Open | bar: 2025-11-16 20
|  |  | Approve | 2025-11-20 | 2025-11-21 | 2 | Open | 2025-11-16 20: Approve
|  | ASSY AUTO: Panel Line*4 (transfer from China) Start date: 11/27 | Line transfer | 2025-10-19 | 2025-11-11 | 23 | On-going | 2025-10-19 20: Line transfer from LH
|  |  | Line setup & Debug | 2025-11-12 | 2025-11-15 | 4 | Open | 2025-11-09 12: Set up & debug
|  |  | Line qual | 2025-11-17 | 2025-11-22 | 6 | Open | 2025-11-16 17: Line qual
|  |  | Trial run | 2025-11-24 | 2025-11-24 | 1 | Open | bar: 2025-11-23 24
|  |  | Approve | 2025-11-24 | 2025-11-25 | 2 | Open | 2025-11-23 24: Approve
5 | Routing machine (de-panel) | Line #1 | Transfer from LH | 2025-11-08 | 2025-11-15 | 8 | On-going | 2025-11-02 8: Delivery
|  |  | Set up | 2025-11-16 | 2025-11-16 | 1 | Open | 2025-11-16 16: Set up
|  |  | Debug | 2025-11-17 | 2025-11-17 | 1 | Open | 2025-11-16 17: Debug
|  |  | Approve | 2025-11-17 | 2025-11-17 | 1 | Open
|  | Line #2 | Transfer from LH | 2025-11-08 | 2025-11-15 | 8 | On-going | 2025-11-02 8: Delivery
|  |  | Set up | 2025-11-16 | 2025-11-16 | 1 | Open | 2025-11-16 16: Set up
|  |  | Debug | 2025-11-17 | 2025-11-17 | 1 | Open | 2025-11-16 17: Debug
|  |  | Approve | 2025-11-17 | 2025-11-17 | 1 | Open | 2025-11-16 17: Approve
6 | Auto HSG assembly | ASSY AUTO: Housing*1 (POR line) Start date: 11/17 | Line setup & Debug | 2025-10-27 | 2025-11-01 | 5 | Closed | 2025-10-26 27: Set up
|  |  | Line qual | 2025-11-03 | 2025-11-09 | 6 | On-going | 2025-11-02 3: Line qual
|  |  | Trial run | 2025-11-12 | 2025-11-12 | 1 | On-going | bar: 2025-11-09 12
|  |  | Approve | 2025-11-10 | 2025-11-12 | 3 | On-going | 2025-11-09 10: Approve
|  | ASSY AUTO: Housing*2 (Retrofit Callie VN HSG line) Start date: 11/24 Pending 2x Link & assemble back housing machine ETA 11/15 | Fixture modification | 2025-10-13 | 2025-11-08 | 26 | Closed | 2025-10-12 13: Fabrication
|  |  | Line setup & Debug | 2025-11-10 | 2025-11-15 | 5 | On-going | 2025-11-09 10: Setup & debug
|  |  | Line qual | 2025-11-17 | 2025-11-19 | 3 | Open | 2025-11-16 17: Line qual
|  |  | Trial run | 2025-11-20 | 2025-11-20 | 1 | Open | bar: 2025-11-16 20
|  |  | Approve | 2025-11-21 | 2025-11-22 | 2 | Open | 2025-11-16 21: Approve
7 | Device testing | Test Line #1 Auto FTS, FPS (Reuse from DVT) | Debug | 2025-10-22 | 2025-10-25 | 4 | Closed | 2025-10-19 22: Debug
|  |  | Line qual | 2025-11-04 | 2025-11-12 | 9 | On-going | 2025-11-02 4: Line qual
|  |  | Trial run | 2025-11-12 | 2025-11-12 | 1 | On-going | bar: 2025-11-09 12
|  |  | Approve | 2025-11-12 | 2025-11-13 | 2 | Open | 2025-11-09 12: Approve
|  | Test Line #2 Auto FTS, FPS (Retrofit from Sheldon VN) | Fixture modification | 2025-09-22 | 2025-10-25 | 33 | Closed | 2025-09-21 22: PR,PO; 2025-09-28 29: Fabrication
|  |  | Line setup & Debug | 2025-10-28 | 2025-11-08 | 11 | Closed | 2025-10-26 28: Setup & debug
|  |  | Line qual | 2025-11-10 | 2025-11-15 | 6 | On-going | 2025-11-09 10: Line qual
|  |  | Trial run | 2025-11-17 | 2025-11-17 | 1 | Open | bar: 2025-11-16 17
|  |  | Approve | 2025-11-17 | 2025-11-18 | 2 | Open | 2025-11-16 17: Approve
|  | Test Line #3 Auto FTS, FPS (Transfer from LH) | Fixture modification | 2025-09-22 | 2025-11-01 | 41 | Closed | 2025-09-21 22: PR,PO; 2025-09-28 29: Fabrication
|  |  | Transfer from LH | 2025-09-15 | 2025-11-06 | 52 | Closed | 2025-09-14 15: Line transfer from LH
|  |  | Line setup & Debug | 2025-11-04 | 2025-11-13 | 9 | On-going | 2025-11-02 4: Setup & debug
|  |  | Line qual | 2025-11-14 | 2025-11-19 | 5 | Open | 2025-11-09 14: Line qual
|  |  | Trial run | 2025-11-20 | 2025-11-20 | 1 | Open | bar: 2025-11-16 20
|  |  | Approve | 2025-11-20 | 2025-11-21 | 2 | Open | 2025-11-16 20: Approve
|  | Test Line #4 Auto FTS, FPS (Transfer from LH) | Fixture modification | 2025-09-22 | 2025-10-29 | 38 | Closed | 2025-09-21 22: PR,PO; 2025-09-28 29: Fabrication
|  |  | Transfer from LH | 2025-09-15 | 2025-11-06 | 52 | Closed | 2025-09-14 15: Line transfer from LH
|  |  | Line setup & Debug | 2025-11-08 | 2025-11-17 | 9 | On-going | 2025-11-02 8: Setup & debug
|  |  | Line qual | 2025-11-18 | 2025-11-22 | 5 | Open | 2025-11-16 18: Line qual
|  |  | Trial run | 2025-11-24 | 2025-11-24 | 1 | Open | bar: 2025-11-23 24
|  |  | Approve | 2025-11-24 | 2025-11-25 | 2 | Open | 2025-11-23 24: Approve
8 | Pack out | CCD Line #1 | Delivery | 2025-11-13 | 2025-11-13 | 1 | Open | 2025-11-09 13: Delivery
|  |  | Set up | 2025-11-14 | 2025-11-15 | 2 | Open | 2025-11-09 14: Set up
|  |  | FIT | 2025-11-17 | 2025-11-18 | 2 | Open | 2025-11-16 17: FIT
|  | CCD Line #2 | Delivery | 2025-11-13 | 2025-11-13 | 1 | Open | 2025-11-09 13: Delivery
|  |  | Set up | 2025-11-14 | 2025-11-15 | 2 | Open | 2025-11-09 14: Set up
|  |  | FIT | 2025-11-19 | 2025-11-20 | 2 | Open | 2025-11-16 19: FIT
|  | CCD Line #3 | Delivery | 2025-11-15 | 2025-11-15 | 1 | Open | 2025-11-09 15: Delivery
|  |  | Set up | 2025-11-17 | 2025-11-18 | 2 | Open | 2025-11-16 17: Set up
|  |  | FIT | 2025-11-24 | 2025-11-25 | 2 | Open | 2025-11-23 24: FIT
|  | CCD Line #4 | Delivery | 2025-11-15 | 2025-11-15 | 1 | Open | 2025-11-09 15: Delivery
|  |  | Set up | 2025-11-17 | 2025-11-18 | 2 | Open | 2025-11-16 17: Set up
|  |  | FIT | 2025-11-27 | 2025-11-28 | 2 | Open | 2025-11-23 27: FIT
|  | CCD Line #5 | Delivery | 2025-11-15 | 2025-11-15 | 1 | Open | 2025-11-09 15: Delivery
|  |  | Set up | 2025-11-17 | 2025-11-18 | 2 | Open | 2025-11-16 17: Set up
|  |  | FIT | 2025-11-29 | 2025-12-01 | 2 | Open | 2025-11-23 29: FIT

## Line Qual Summary
Calypso VN PVT SMT and FATP Line Setup and Qualification Schedule
Station | Qualifiation item | Oct | [30 empty] | Nov | [29 empty] | Dec
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SMT | SMT Line qualification (CPK+GRR) S2 | Nov 7: Setup; Nov 10: Debug; Nov 12: Customer approval; Nov 14: ※PVT
| SMT Line qualification (CPK+GRR) S12 | Nov 23: Setup; Nov 24: Debug; Nov 25: ※PVT
| SMT Line qualification (CPK+GRR) S1 | Nov 24: Setup; Nov 25: Debug; Nov 26: ※PVT
Test Station BFT Line1 BF T * 4 | Strain Gauge + GRR + Correlation | Oct 22: Debug; Nov 3: Line qualificaiton (Strain Gauge + GRR + Correlation); Nov 11: Customer approval; Nov 17: ※PVT
Test Station BFT Line2 BFT*4 | Strain Gauge + GRR + Correlation | Oct 27: Set up & debug; Nov 10: Line qualificaiton (Strain Gauge + GRR + Correlation); Nov 15: Customer approval; Nov 20: ※PVT
Test Station BFT Line3 BFT*4 | Strain Gauge + GRR + Correlation | Oct 30: Set up & debug; Nov 13: Line qualificaiton (Strain Gauge + GRR + Correlation); Nov 19: Customer approval; Nov 24: ※PVT
Test Station BFT Line4 BFT*4 | Strain Gauge + GRR + Correlation | Nov 3: Set up & debug; Nov 17: Line qualificaiton (Strain Gauge + GRR + Correlation); Nov 22: Customer approval; Nov 27: ※PVT
ASSY AUTO: Panel Line*4 | Auto Fungible 1.0 Assy line1 (POR line) | Oct 27: Setup ready; Nov 3: Line qualificaiton (Force CPK + Paper test+ Strain gauge; Nov 12: Trial run; Nov 13: Customer approval; Nov 15: FAI build; Nov 17: ※PVT
| Auto Fungible 1.0 Assy line 2 | Nov 7: Setup ready; Nov 12: Line qualificaiton (Force CPK + Paper test+ Strain gauge); Nov 17: Customer approval; Nov 20: ※PVT
| Auto Fungible 1.0 Assy line 3 | Oct 20: Line transfer from LH; Nov 10: Setup ready; Nov 15: Line qualificaiton (Force CPK + Paper test+ Strain gauge); Nov 20: Customer approval; Nov 24: ※PVT
| Auto Fungible 1.0 Assy line 4 | Oct 20: Line transfer from LH; Nov 12: Setup ready; Nov 17: Line qualificaiton (Force CPK + Paper test+ Strain gauge); Nov 24: Customer approval; Nov 27: ※PVT
ASSY AUTO: Housing*2 | Auto Fungible 2.0 Assy line1 (POR line) | Oct 27: Setup ready; Nov 3: Line qualificaiton (Force Cpk+Paper test+ Strain gauge); Nov 11: Customer approval; Nov 17: ※PVT
| Auto Fungible 2.0 Assy line2 (Retrofit Callie VN HSG line) | Nov 10: Set up & debug; Nov 17: Line qualification; Nov 21: Customer approval; Nov 24: ※PVT
Test Station FTS Line1 FTS * 2 Cell (12+12) | GRR + Correlation | Oct 22: Debug; Nov 4: Line qualificaiton (GRR + Correlation); Nov 12: Customer approval; Nov 17: ※PVT
Test Station FPS Line1 FPS * 4 | Loop Test | Oct 22: Debug; Nov 4: Line qualificaiton (GRR + Correlation); Nov 12: Customer approval; Nov 17: ※PVT
Test Station FTS Line2 FTS * 2Cell (12+12) | GRR + Correlation | Oct 28: Set up & debug; Nov 10: Line qualificaiton (GRR + Correlation); Nov 17: Customer approval; Nov 20: ※PVT
Test Station FPS Line2 FPS*4 | Loop Test | Oct 28: Set up & debug; Nov 10: Line qualificaiton (GRR + Correlation); Nov 17: Customer approval; Nov 20: ※PVT
Test Station FTS Line3 FTS*2Cell (12+12) | GRR + Correlation | Nov 4: Set up & debug; Nov 14: Line qualificaiton (GRR + Correlation); Nov 20: Customer approval; Nov 24: ※PVT
Test Station FPS Line3 FPS*4 | Loop Test | Nov 4: Set up & debug; Nov 14: Line qualificaiton (GRR + Correlation); Nov 20: Customer approval; Nov 24: ※PVT
Test Station FTS Line4 FTS*2Cell (12+12) | GRR + Correlation | Nov 8: Set up & debug; Nov 18: Line qualificaiton (GRR + Correlation); Nov 24: Customer approval; Nov 27: ※PVT
Test Station FPS Line4 FPS*4 | Loop Test | Nov 8: Set up & debug; Nov 18: Line qualificaiton (GRR + Correlation); Nov 24: Customer approval; Nov 27: ※PVT
Pack out line #1 Manual | VI Station (Fault injection) | Nov 14: Setup; Nov 17: FIT; Nov 19: ※PVT
Pack out line #2 Manual | VI Station (Fault injection) | Nov 14: Setup; Nov 19: FIT; Nov 21: ※PVT
Pack out line #3 Manual | VI Station (Fault injection) | Nov 17: Setup; Nov 24: FIT; Nov 26: ※PVT
Pack out line #4 Manual | VI Station (Fault injection) | Nov 17: Setup; Nov 27: FIT; Nov 29: ※PVT
Pack out line #5 Manual | VI Station (Fault injection) | Nov 17: Setup; Nov 29: FIT; Dec 2: ※PVT

## OBA Readiness
OBA Readiness Review for PVT
No. | Contents | PVT |  | Remark
| Contents | Status | Due date | Remark
1 | Product build Milestone | Closed | 2025-10-10 | Follow up OPM Build Matrix
2 | Escalation List | Closed | 2025-09-19
3 | OBA Facility Check List | Closed | 2025-11-10 | Add 3 Shielding rooms with TV and fixture to Calypso: - Onhand 3 Shielding rooms - Already Moved 3 Shielding rooms to Calypso, on-going to setup electric, network, TV.
4 | OBA Layout | Closed | 2025-11-10 | Set up shielding room and setup to Calypso
5 | OBA Operator Training Plan | on-going | 2025-11-15 | Start from 11/08, complete by 11/15
6 | SIP - based on TCD | Closed | 2025-10-27 | Update SIP based on new OBA TCD provide by DQM.
7 | OBA Capacity--OBA | Closed | 2025-10-10
8 | CET Plan | Closed | 2025-11-10
9 | Weekly Review action item list | Closed | Daily
10 | OBA PVT Regression test | Closed | 2025-11-01 | GMC regression test user image 19
Summary:
No risk

## IQC Readiness
Calypso IQC Readiness Summary
No. | Items | CM/AMZ DRI | Due date | Status
1 | MMIL(Material Major Issue list) through build | Tongzhang/Evan | 2025-10-18 | Closed | All material issues have been closed
2 | Team list | Tongzhang/Evan | 2025-01-08 | Closed
3 | Project schedule | Tongzhang/Evan | 2025-01-08 | Closed
4 | Key part list&material ETA&IQC plan | Tongzhang/Evan | 2025-01-08 | Closed
5 | Key parts vendors OQC/IQC alignment | Tongzhang/Evan | 2025-01-26 | Closed
6 | SIP/MSOP readiness | Tongzhang/Evan | 2025-08-16 | Closed
7 | Reference/Limit/Golden/Construction samples list | Tongzhang/Evan | 2025-10-18 | Closed | PVT golden and limit sample ID has been signed
8 | Equipment/Fixture readiness | Tongzhang/Evan | 2025-01-08 | Closed
9 | IQC inspector list/training | Tongzhang/Evan | 2025-01-08 | Closed
10 | Measurement&Inspection Qualification(GRR/ARR & Correlation) | Tongzhang/Evan | 2025-11-10 | Closed | IQC need to do ARR follow limit sample
11 | Supplier audit plan(For key Non-A parts) | Tongzhang/Evan | 2025-01-08 | Closed
12 | SI arrange plan(For key ME parts) | Tongzhang/Evan | 2025-11-10 | Closed | Arrange VN IQC team go to VN N.W.E SI.
13 | Material vendor on-site support plan | Tongzhang/Evan | 2025-01-08 | Closed
14 | Material vendor sorting area & capacity | Tongzhang/Evan | 2025-01-08 | Closed

## DGL pre-launch
Calypso | Pre-Lauch Checking List
OK to ship day: | 2025-12-08
Planned first ship day: | 2025-12-10
*CM needs to consult with CMM on which column (D or E) when working on new program checklist
Updated by CM
Category | Item | Start Date | Device PIC | Remark | Parking lot | Weekly Status | Weekly Highlights
CM Checking List | Vendor Code /Customer Code | 2 month before OK2S | OEM |  |  | Completed
| DTMS configuration setup checking for Manual ASIN weights and DIMS, Program configuration, Vendor configuration | 4 weeks before ok2ship | N/A to device |  |  | N/A | Not required for Devices
| SSCC pre-fix apply with GS1(new CM) | 2 months before OK2ship | DGL NPI |  |  | Completed
| Ring: SSCC requirement with complaince checking | 4 weeks before ok2ship |  |  |  | N/A | Not required for Devices
| Check whether Leather Contained or not, if yes, check Leather source with vendor, get prepared to issue Declaration of Leather source for shipment to India and Italy, get prepared to issue COO for India. | 2 month before OK2Ship | MM |  |  | N/A | No leather
| Battery Documents (UN38.3, MSDS, 3M Drop Test) & Device level Certificate(Safe Transportation Certificate), DG license & process (if any) Readiness and send to LSPs for pre-check, details refer to SOP 4.3 attachment | 1 month before OK2Ship | DGL CMM |  |  | Completed | Have enough MSDS, Test report. No requirement for 3M Drop test.
| For Magnet document (MSDS / Magnet testing report/Safe Transportation Certificate) | 1 month before OK2S | DGL CMM |  |  | N/A | Non-magnetic Dry battery only
| CM logistics are required to check the new project whether include below sensitive materials (refer to a sensitive materials in file 4.3 master check list) which may impact the product transportation and need prepare the related certificate to forwarder to check for booking acceptance in advance. | 1 month before OK2S | CM | Sensitive materials 含液体的产品 - Liquid 含磁的产品 - Magnetism 含电池的产品 – battery 含有马达的电器 – Motor 含有粉末 – Powder 化学物质 - Chemicals 含爆炸易燃 - the inflammables and explosives |  | Completed | Dry battery only
| BOM & Customs registration Readiness | 1 week before OK2SHIP | CM |  |  | In progress | Due date: 28-Nov-2025
| Shipment in/to CN FCs (if any) Process Review | 2 month before okship | DGL CMM |  |  | In progress | Due date: 20-Nov-2025
| Pallet type Matrix Check in Agile | 1 month before okship | DGL NPI |  |  | Completed | Follow Pallet Matrix 05-000818 ver 28
| Vendor Central PO Receiving | 1 month before okship | FP |  |  | Completed | PO received
| HTS code & PD readiness | 1 month before okship | Global Trade Compliance |  |  | Completed
| Check ECCN for shipment to IC2S/ICA2 (MX, AU, BR OFFLINE) | 1 month before okship | Global Trade Compliance |  |  | In progress | Due date: 20-Nov-2025
| Authorization Letter / IPR registration (if applicable) | 1 month before okship | Global Trade Compliance |  |  | N/A | In Vietnam: inapplicable
| Booking for the first shipment | per timeline of different ship mode | DGL CMM |  |  | Not start | Due date: 26-Nov-2025
| Check internal counterpart whether FCC certificate was granted for US shipments. | 1 month before okship | DGL NPI |  |  | In progress | Due date: 20-Nov-2025
| Check internal counterpart whether ISED certificate was granted for Canada shipments. | 1 month before ok2ship | DGL NPI |  |  | In progress | Due date: 20-Nov-2025
| Check internal counterpart whether WPC import license and AAR filing ready for India shipments | 1 month before ok2ship | DGL NPI |  |  | In progress | Due date: 20-Nov-2025
| Ring: Pallet packing reliability testing passing confirmation: viabration reliability testing, static storage simulation testing, truck loading/unloading simulation testing, and etc. | 1 month before ok2ship | N/A to device |  |  | N/A | No requirement for Devices
| Ring: Ring carton and pallet label guide confirmation: please refer to the doc of "5-026425-11_Ring_PACK_LabelGuide_v11a" | 1 month before ok2ship | N/A to device |  |  | N/A | No requirement for Devices
| Ring: Adile BOM readiness checking | 1 month before ok2ship | N/A to device |  |  | N/A | No requirement for Devices
| Product packing information confirmation: (1) carton and pallet packing design frozen confirmation, (2) Carton and pallet packing SOP confirmation, (3) pallet usage matrix confirmation, (4) all kinds of length/wedith/height dimension and weight information confirmation, (5) carton and pallet SSCC bar code design confirmation, (6) double pallet stacking design confirmation. (7) Ring - Retail box design drawing passed | 4 weeks before ok2ship | N/A to device |  |  | N/A | No requirement for Devices
| Required documents for shipping: 1. MSDS documents for dry batteries 2. Test Reports for dry batteries 3. Letters of Indemnity confirming that our batteries comply with the rules for transportation of dangerous goods | per shipment | OEM | Already on hand |  | Completed
Completed
In progress
Not start
N/A

## OP Trainning plan
Stage | Process | Training contents | Line | OP qty | OP Hiring | Ops On Board | Training date | OP Training Report | Online | Status
PVT | SMT | a. ESD/ occupational safety b.Feed PCB board c.Machine operation d.Abnormal handing e.Form check f.VI | Line S2 | 8 | / | / | 2025/11/05 - 2025/11/10 | 2025-11-12 | 2025-11-14 | Line is allocating for other projects
|  |  | Line S12 | 8 | / | / | 2025/11/18 - 2025/11/23 | 2025-11-24 | 2025-11-25 | Line is allocating for other projects
|  |  | Line S1 | 8 | / | / | 2025/11/19- 2025/11/24 | 2025-11-25 | 2025-11-26 | Line is allocating for other projects
| BFT | a. ESD/ occupational safety b. Feed PCBA board c. Machine operation d. Abnormal handing e. Form check f. VI | Line 1 ~ Line 4 | 1 | / | / | 2025/11/08-2025/11/11 | 2025-11-12 | 2025-11-14 | Follow SMT line start date
| Routing | PCBA routing | Routing machine | / | / | / | 2025/11/11-2025/11/14 | 2025-11-14 | 2025-11-17
| Assembly & Test | a. ESD/ occupational safety b. Fixture operation c. Abnormal handing d. Form check e. VI | Line1 | 7 | / | / | 2025/11/11-2025/11/14 | 2025-11-14 | 2025-11-17
|  |  | Line2 | 7 | / | / | 2025/11/13-2025/11/17 | 2025-11-18 | 2025-11-20
|  |  | Line 3 | 7 | / | / | 2025/11/17-2025/11/20 | 2025-11-21 | 2025-11-24
|  |  | Line 4 | 7 | / | / | 2025/11/20-2025/11/24 | 2025-11-25 | 2025-11-27
| PACKING | a.SOP learning b.Abnormal handing c.Form check d.VI | Manual line 1 | 13 | / | / | 2025/11/11-2025/11/14 | 2025-11-15 | 2025-11-18
|  |  | Manual line 2 | 13 | / | / | 2025/11/13-2025/11/17 | 2025-11-18 | 2025-11-20
|  |  | Manual line 3 | 13 | / | / | 2025/11/18-2025/11/21 | 2025-11-22 | 2025-11-25
|  |  | Manual line 4 | 13 | / | / | 2025/11/21-2025/11/25 | 2025-11-26 | 2025-11-28
|  |  | Manual line 5 |  | / | / | 2025/11/24-2025/11/27 | 2025-11-28 | 2025-12-01

## VN layout (hidden)
1. SMT LAYOUT
2. FATP LAYOUT
Remark: Move packing POR line next to left over 4 packing lines after DVT for PVT
SMT S1
SMT S2
SMT S12
Packing line * 4M
Manual line
Auto line * 4
Packing line * 1M
Packing line * 1A

## Reports for OK2S (hidden)
PVT Data cut off:
No | Type of report | Passing criteria | Test requirement | Submit Time | ETC/Approval | CNT DRI | AMZ DRI | Status | Remark | File
1 | ORT |  | ORT pick up plan 10pcs PCBA+100pcs device | Sample pick up from 3/27, test time last 2 weeks |  | Quinn | JINJUN |  | PCBA pick up date: 3/27 (10pcs) Line 1# day shift pick up date: 4/1 50pcs Line 1# night shift pick up date: 4/1 50pcs
2 | IQC |  | will daily update in the PVT open/close meeting | daily tracking and update | - | PM Wanda | FMQM Cotton
3 | SMT |  | will daily update in the PVT open/close meeting | daily tracking and update | - | PQE Estellle | SMT STM Dong
4 | FATP |  | will daily update in the PVT open/close meeting | daily tracking and update | - | PQE Estellle | FATP STM Duke
5 | 53- FAI report |  | material/PN are correct | 2025-04-07 | 2025-04-08 | PKG RD Meredith | STM Duke / DQM Phil
6 | cross section |  |  | 4/8~4/22 | 2025-04-24 | ME Yandong | SMT STM Dong
7 | OP training |  | OP qualified for production |  | 2025-04-05 | PM Wanda | SMT STM Dong/FATP STM Duke
8 | CET Test |  | *CET plan in PVT: Callie : 6 pallets | Estimate CET test time: 12days - Pre-Seal test before: 7days (4/7-4/15) - Packout 6 pallets : 1 day (4/16) - CET test: 1 day (4/17) - Post CET: 1 days (4/18). - Make report : 2 day(Post CET&Aging report) (4/22) | 2025-04-23 | PQE Estellle | DQM Phil Chen | On-going | Estimate time CET pick up start from 4/9
9 | OBA |  | Update new sampling rate check in PVT: 1. Pre-seal (devices): 663 first pcs with new line/shift, then switch to 3.4% (line UPH 498). 2.1 OBA3(Box-Accessories) : 438 first pcs with new line/shift, then switch to 4% for Manual packing line (UPH 411). 2.2 OBA take 25 sets of accessories (Adapter, HDMI cable, Micro USB cable will be checked function at the beginning of every working day. 3. Post-seal: 6 pcs/line/shift (3pcs/line/shift to test without Aquila, 3pcs/line/shift to test Aquila only) | Line1(UPH 498) start on 2025/4/7 Line2(UPH 498) start on 2025/4/10 | OK2S 2025/4/30 | PQE Estellle | DQM Phil Chen | On-going
10 | Teardown audit |  | Callie : 1pc | 2025-04-10 | 2025-04-11 | PQE Estellle | DQM Phil Chen | On-going | Estimate time

## Ramp up plan by line
Calypso- PVT/MP SMT input Plan | [23 empty] | Cut off data | Submit reports | Review reports |  |  |  |  | OK2Ship |  | FFS
|  | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
|  | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13
SMT S2 (6H2G) | [6 empty] | 204 | 2400 |  | 4800 | 9600 | 12000 | 12000 | 12000 | 12000 |  | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 |  | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 |  | 12000 | 12000 | 12000 | 12000 | 12000 | 12000
SMT S12 (5H2G) |  | 2025-11-22: ETA; 2025-11-25: 204; 2025-11-26: 2400; 2025-11-27: 4800; 2025-11-28: 9600; 2025-11-29: 12000; 2025-12-01: 12000; 2025-12-02: 12000; 2025-12-03: 12000; 2025-12-04: 12000; 2025-12-05: 12000; 2025-12-06: 12000; 2025-12-08: 12000; 2025-12-09: 12000; 2025-12-10: 12000; 2025-12-11: 12000; 2025-12-12: 12000; 2025-12-13: 12000
SMT S1 (6H2G) |  | 2025-11-22: ETA; 2025-11-26: 204; 2025-11-27: 2400; 2025-11-28: 4800; 2025-11-29: 9600; 2025-12-01: 12000; 2025-12-02: 12000; 2025-12-03: 12000; 2025-12-04: 12000; 2025-12-05: 12000; 2025-12-06: 12000; 2025-12-08: 12000; 2025-12-09: 12000; 2025-12-10: 12000; 2025-12-11: 12000; 2025-12-12: 12000; 2025-12-13: 12000
Daily SMT capacity | [5 empty] | 0 | 204 | 2400 | 0 | 4800 | 9600 | 12000 | 12000 | 12000 | 12000 | 0 | 12000 | 12204 | 14604 | 19200 | 26400 | 33600 | 0 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 0 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000
CUM SMT capacity | [5 empty] | 0 | 204 | 2604 | 2604 | 7404 | 17004 | 29004 | 41004 | 53004 | 65004 | 65004 | 77004 | 89208 | 103812 | 123012 | 149412 | 183012 | 183012 | 219012 | 255012 | 291012 | 327012 | 363012 | 399012 | 399012 | 435012 | 471012 | 507012 | 543012 | 579012 | 615012
Calypso- PVT/MP FATP input Plan |  | 2025-12-01: Cut off data; 2025-12-02: Submit reports; 2025-12-03: Review reports; 2025-12-08: OK2Ship; 2025-12-10: FFS
| Shift | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
|  | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13
Fungible 1.0*UPH*498-Line 1 | DS |  |  |  | 60 |  |  | 24 |  | 723 | Yield review | 964 | 1446 | 1929 | 2411 | 0 | 2893 | 3375 | 3858 | 4099 | 4340 | 4581 | 0 | 4581 | 4581 | 4581 | 4581 | 4581 | 4581 | 0 | 4581 | 4581 | 4581 | 4581 | 4581 | 4581
| NS | [9 empty] | 664 | Yield review | 886 | 1329 | 1772 | 0 | 2215 | 2659 | 3102 | 3545 | 3766 | 3988 | 0 | 4210 | 4210 | 4210 | 4210 | 4210 | 4210 | 0 | 4210 | 4210 | 4210 | 4210 | 4210 | 4210
Fungible 1.0*UPH*498-Line 2 | DS | [8 empty] | 60 |  |  | 723 | Yield review | 964 | 0 | 1446 | 1929 | 2411 | 2893 | 3375 | 3858 | 0 | 4099 | 4340 | 4581 | 4581 | 4581 | 4581 | 0 | 4581 | 4581 | 4581 | 4581 | 4581 | 4581
| NS | [12 empty] | 664 | Yield review |  | 886 | 1329 | 1772 | 2215 | 2659 | 3102 | 0 | 3545 | 3766 | 3988 | 4210 | 4210 | 4210 | 0 | 4210 | 4210 | 4210 | 4210 | 4210 | 4210
Fungible 1.0*UPH*498-Line 3 | DS | [11 empty] | 60 |  |  |  | 723 | Yield review | 964 | 1446 | 1929 | 2411 | 0 | 2893 | 3375 | 3858 | 4099 | 4340 | 4581 | 0 | 4581 | 4581 | 4581 | 4581 | 4581 | 4581
| NS | 2025-11-25: 664; 2025-11-26: Yield review; 2025-11-27: 886; 2025-11-28: 1329; 2025-11-29: 1772; 2025-11-30: 0; 2025-12-01: 2215; 2025-12-02: 2659; 2025-12-03: 3102; 2025-12-04: 3545; 2025-12-05: 3766; 2025-12-06: 3988; 2025-12-07: 0; 2025-12-08: 4210; 2025-12-09: 4210; 2025-12-10: 4210; 2025-12-11: 4210; 2025-12-12: 4210; 2025-12-13: 4210
Fungible 1.0*UPH*498-Line 4 | DS | 2025-11-24: 60; 2025-11-27: 723; 2025-11-28: Yield review; 2025-11-29: 964; 2025-11-30: 0; 2025-12-01: 1446; 2025-12-02: 1929; 2025-12-03: 2411; 2025-12-04: 2893; 2025-12-05: 3375; 2025-12-06: 3858; 2025-12-07: 0; 2025-12-08: 4099; 2025-12-09: 4340; 2025-12-10: 4581; 2025-12-11: 4581; 2025-12-12: 4581; 2025-12-13: 4581
| NS | 2025-11-28: 664; 2025-11-29: Yield review; 2025-11-30: 0; 2025-12-01: 886; 2025-12-02: 1329; 2025-12-03: 1772; 2025-12-04: 2215; 2025-12-05: 2659; 2025-12-06: 3102; 2025-12-07: 0; 2025-12-08: 3545; 2025-12-09: 3766; 2025-12-10: 3988; 2025-12-11: 4210; 2025-12-12: 4210; 2025-12-13: 4210
| Total |  |  |  | 60 | 0 | 0 | 24 | 0 | 783 | 664 | 964 | 3115 | 3922 | 5147 | 0 | 8223 | 9956 | 12107 | 15807 | 18062 | 20676 | 0 | 23875 | 26189 | 28503 | 30334 | 31722 | 33111 | 0 | 34017 | 34479 | 34942 | 35164 | 35164 | 35164
| Cum total |  |  |  | 60 | 60 | 60 | 84 | 84 | 867 | 1531 | 2495 | 5610 | 9532 | 14679 | 14679 | 22902 | 32858 | 44965 | 60772 | 78834 | 99510 | 99510 | 123385 | 149574 | 178077 | 208411 | 240133 | 273244 | 273244 | 307261 | 341740 | 376682 | 411846 | 447010 | 482174
| WIP(MLB) | [5 empty] | 144 | 2520 | 2520 | 6537 | 15473 | 26509 | 35394 | 43472 | 50325 | 50325 | 54102 | 56350 | 58847 | 62240 | 70578 | 83502 | 83502 | 95627 | 105438 | 112935 | 118601 | 122879 | 125768 | 125768 | 127751 | 129272 | 130330 | 131166 | 132002 | 132838
| SMT WIP VS Daily demand | [6 empty] | 105 |  | 8.3487 | 23.3027 | 27.499 | 11.3624 | 11.0841 | 9.7775 |  | 6.5794 | 5.6599 | 4.8606 | 3.9375 | 3.9075 | 4.0386 |  | 4.0053 | 4.026 | 3.9622 | 3.9098 | 3.8736 | 3.7984 |  | 3.7555 | 3.7493 | 3.7299 | 3.7301 | 3.7539 | 3.7777
Efficiency | Plan lines | [8 empty] | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4
| Plan shifts | [8 empty] | 2 | 1 | 1 | 4 | 3 | 3 | 3 | 6 | 5 | 5 | 7 | 7 | 7 |  | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8
Fungible 1.0*UPH*498-Line 1 | DS | [6 empty] | FAI |  | 15% | Yield review | 20% | 30% | 40% | 50% |  | 60% | 70% | 80% | 85% | 90% | 95% |  | 95% | 95% | 95% | 95% | 95% | 95% |  | 95% | 95% | 95% | 95% | 95% | 95%
| NS | [9 empty] | 15% | Yield review | 20% | 30% | 40% |  | 50% | 60% | 70% | 80% | 85% | 90% |  | 95% | 95% | 95% | 95% | 95% | 95% |  | 95% | 95% | 95% | 95% | 95% | 95%
Fungible 1.0*UPH*498-Line 2 | DS | [11 empty] | 15% | Yield review | 20% |  | 30% | 40% | 50% | 60% | 70% | 80% |  | 85% | 90% | 95% | 95% | 95% | 95% |  | 95% | 95% | 95% | 95% | 95% | 95%
| NS | 2025-11-21: 15%; 2025-11-22: Yield review; 2025-11-24: 20%; 2025-11-25: 30%; 2025-11-26: 40%; 2025-11-27: 50%; 2025-11-28: 60%; 2025-11-29: 70%; 2025-12-01: 80%; 2025-12-02: 85%; 2025-12-03: 90%; 2025-12-04: 95%; 2025-12-05: 95%; 2025-12-06: 95%; 2025-12-08: 95%; 2025-12-09: 95%; 2025-12-10: 95%; 2025-12-11: 95%; 2025-12-12: 95%; 2025-12-13: 95%
Fungible 1.0*UPH*498-Line 3 | DS | 2025-11-24: 15%; 2025-11-25: Yield review; 2025-11-26: 20%; 2025-11-27: 30%; 2025-11-28: 40%; 2025-11-29: 50%; 2025-12-01: 60%; 2025-12-02: 70%; 2025-12-03: 80%; 2025-12-04: 85%; 2025-12-05: 90%; 2025-12-06: 95%; 2025-12-08: 95%; 2025-12-09: 95%; 2025-12-10: 95%; 2025-12-11: 95%; 2025-12-12: 95%; 2025-12-13: 95%
| NS | 2025-11-25: 15%; 2025-11-26: Yield review; 2025-11-27: 20%; 2025-11-28: 30%; 2025-11-29: 40%; 2025-12-01: 50%; 2025-12-02: 60%; 2025-12-03: 70%; 2025-12-04: 80%; 2025-12-05: 85%; 2025-12-06: 90%; 2025-12-08: 95%; 2025-12-09: 95%; 2025-12-10: 95%; 2025-12-11: 95%; 2025-12-12: 95%; 2025-12-13: 95%
Fungible 1.0*UPH*498-Line 4 | DS | 2025-11-27: 15%; 2025-11-28: Yield review; 2025-11-29: 20%; 2025-12-01: 30%; 2025-12-02: 40%; 2025-12-03: 50%; 2025-12-04: 60%; 2025-12-05: 70%; 2025-12-06: 80%; 2025-12-08: 85%; 2025-12-09: 90%; 2025-12-10: 95%; 2025-12-11: 95%; 2025-12-12: 95%; 2025-12-13: 95%
| NS | 2025-11-28: 15%; 2025-11-29: Yield review; 2025-12-01: 20%; 2025-12-02: 30%; 2025-12-03: 40%; 2025-12-04: 50%; 2025-12-05: 60%; 2025-12-06: 70%; 2025-12-08: 80%; 2025-12-09: 85%; 2025-12-10: 90%; 2025-12-11: 95%; 2025-12-12: 95%; 2025-12-13: 95%
| Working hour | [8 empty] | 19 | 9.5 | 9.5 | 38 | 28.5 | 28.5 | 28.5 | 57 | 47.5 | 47.5 | 66.5 | 66.5 | 66.5 | 0 | 76 | 76 | 76 | 76 | 76 | 76 | 0 | 76 | 76 | 76 | 76 | 76 | 76
Calypso- PVT/MP Packout input Plan |  | 2025-12-08: OK2Ship; 2025-12-10: FFS
| Shift | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
|  | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13
Manual Packing - Line 1 | DS |  |  |  |  | 12 |  |  |  |  | 12 | 760 | 1140 | 1520 | 1900 |  | 2281 | 2661 | 3041 | 3231 | 3421 | 3611 |  | 3801 | 3801 | 3801 | 3801 | 3801 | 3801 | 0 | 3801 | 3801 | 3801 | 3801 | 3801 | 3801
| NS | [11 empty] | 698 | 1048 | 1397 |  | 1746 | 2096 | 2445 | 2794 | 2969 | 3144 |  | 3318 | 3493 | 3493 | 3493 | 3493 | 3493 | 0 | 3493 | 3493 | 3493 | 3493 | 3493 | 3493
Manual Packing - Line 2 | DS | [8 empty] | 12 |  |  | 12 | 760 | 1140 |  | 1520 | 1900 | 2281 | 2661 | 3041 | 3231 |  | 3421 | 3611 | 3801 | 3801 | 3801 | 3801 | 0 | 3801 | 3801 | 3801 | 3801 | 3801 | 3801
| NS | 2025-11-22: 698; 2025-11-24: 1048; 2025-11-25: 1397; 2025-11-26: 1746; 2025-11-27: 2096; 2025-11-28: 2445; 2025-11-29: 2794; 2025-12-01: 2969; 2025-12-02: 3144; 2025-12-03: 3318; 2025-12-04: 3493; 2025-12-05: 3493; 2025-12-06: 3493; 2025-12-07: 0; 2025-12-08: 3493; 2025-12-09: 3493; 2025-12-10: 3493; 2025-12-11: 3493; 2025-12-12: 3493; 2025-12-13: 3493
Manual Packing - Line 3 | DS | 2025-11-21: 12; 2025-11-25: 12; 2025-11-26: 760; 2025-11-27: 1140; 2025-11-28: 1520; 2025-11-29: 1900; 2025-12-01: 2281; 2025-12-02: 2661; 2025-12-03: 3041; 2025-12-04: 3231; 2025-12-05: 3421; 2025-12-06: 3623; 2025-12-07: 0; 2025-12-08: 3801; 2025-12-09: 3801; 2025-12-10: 3801; 2025-12-11: 3801; 2025-12-12: 3801; 2025-12-13: 3801
| NS | 2025-11-27: 698; 2025-11-28: 1048; 2025-11-29: 1397; 2025-12-01: 1746; 2025-12-02: 2096; 2025-12-03: 2445; 2025-12-04: 2794; 2025-12-05: 2969; 2025-12-06: 3154; 2025-12-07: 0; 2025-12-08: 3318; 2025-12-09: 3493; 2025-12-10: 3493; 2025-12-11: 3493; 2025-12-12: 3493; 2025-12-13: 3493
Manual Packing - Line 4 | DS | 2025-11-25: 12; 2025-11-28: 12; 2025-11-29: 760; 2025-12-01: 1140; 2025-12-02: 1520; 2025-12-03: 1900; 2025-12-04: 2281; 2025-12-05: 2661; 2025-12-06: 3052; 2025-12-07: 0; 2025-12-08: 3231; 2025-12-09: 3421; 2025-12-10: 3611; 2025-12-11: 3801; 2025-12-12: 3801; 2025-12-13: 3801
| NS | 2025-12-01: 698; 2025-12-02: 1048; 2025-12-03: 1397; 2025-12-04: 1746; 2025-12-05: 2096; 2025-12-06: 2455; 2025-12-07: 0; 2025-12-08: 2794; 2025-12-09: 2969; 2025-12-10: 3144; 2025-12-11: 3318; 2025-12-12: 3493; 2025-12-13: 3493
Manual Packing - Line 5 | DS | 2025-11-26: 12; 2025-12-01: 12; 2025-12-02: 760; 2025-12-03: 1140; 2025-12-04: 1520; 2025-12-05: 1900; 2025-12-06: 2292; 2025-12-07: 0; 2025-12-08: 2661; 2025-12-09: 3041; 2025-12-10: 3231; 2025-12-11: 3421; 2025-12-12: 3611; 2025-12-13: 3801
| NS | 2025-12-03: 698; 2025-12-04: 1048; 2025-12-05: 1397; 2025-12-06: 1755; 2025-12-07: 0; 2025-12-08: 2096; 2025-12-09: 2445; 2025-12-10: 2794; 2025-12-11: 2969; 2025-12-12: 3144; 2025-12-13: 3318
| Total daily |  |  |  |  | 12 |  |  |  | 12 | 12 | 760 | 1850 | 3340 | 5135 | 0 | 6595 | 8078 | 10285 | 12620 | 14456 | 16837 | 0 | 19386 | 22134 | 25034 | 27208 | 29032 | 30919 | 0 | 32489 | 33758 | 34662 | 35391 | 35931 | 36295
| Cum total |  |  |  |  | 12 | 12 | 12 | 12 | 24 | 36 | 796 | 2646 | 5986 | 11121 | 11121 | 17716 | 25794 | 36079 | 48699 | 63155 | 79992 | 79992 | 99378 | 121512 | 146546 | 173754 | 202786 | 233705 | 233705 | 266194 | 299952 | 334614 | 370005 | 405936 | 442231
| WIP | [8 empty] | 843 | 1495 | 1699 | 2964 | 3546 | 3558 | 3558 | 5186 | 7064 | 8886 | 12073 | 15679 | 19518 | 19518 | 24007 | 28062 | 31531 | 34657 | 37347 | 39539 | 39539 | 41067 | 41788 | 42068 | 41841 | 41074 | 39943
Manual Packing - Line 1 | DS | [9 empty] | FAI | 20% | 30% | 40% | 50% |  | 60% | 70% | 80% | 85% | 90% | 95% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100%
| NS | [11 empty] | 20% | 30% | 40% |  | 50% | 60% | 70% | 80% | 85% | 90% |  | 95% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100%
Manual Packing - Line 2 | DS | [11 empty] | FAI | 20% | 30% |  | 40% | 50% | 60% | 70% | 80% | 85% |  | 90% | 95% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100%
| NS | 2025-11-22: 20%; 2025-11-24: 30%; 2025-11-25: 40%; 2025-11-26: 50%; 2025-11-27: 60%; 2025-11-28: 70%; 2025-11-29: 80%; 2025-12-01: 85%; 2025-12-02: 90%; 2025-12-03: 95%; 2025-12-04: 100%; 2025-12-05: 100%; 2025-12-06: 100%; 2025-12-08: 100%; 2025-12-09: 100%; 2025-12-10: 100%; 2025-12-11: 100%; 2025-12-12: 100%; 2025-12-13: 100%
Manual Packing - Line 3 | DS | 2025-11-25: FAI; 2025-11-26: 20%; 2025-11-27: 30%; 2025-11-28: 40%; 2025-11-29: 50%; 2025-12-01: 60%; 2025-12-02: 70%; 2025-12-03: 80%; 2025-12-04: 85%; 2025-12-05: 90%; 2025-12-06: 95.3%; 2025-12-08: 100%; 2025-12-09: 100%; 2025-12-10: 100%; 2025-12-11: 100%; 2025-12-12: 100%; 2025-12-13: 100%
| NS | 2025-11-27: 20%; 2025-11-28: 30%; 2025-11-29: 40%; 2025-12-01: 50%; 2025-12-02: 60%; 2025-12-03: 70%; 2025-12-04: 80%; 2025-12-05: 85%; 2025-12-06: 90.3%; 2025-12-08: 95%; 2025-12-09: 100%; 2025-12-10: 100%; 2025-12-11: 100%; 2025-12-12: 100%; 2025-12-13: 100%
Manual Packing - Line 4 | DS | 2025-11-28: FAI; 2025-11-29: 20%; 2025-12-01: 30%; 2025-12-02: 40%; 2025-12-03: 50%; 2025-12-04: 60%; 2025-12-05: 70%; 2025-12-06: 80.3%; 2025-12-08: 85%; 2025-12-09: 90%; 2025-12-10: 95%; 2025-12-11: 100%; 2025-12-12: 100%; 2025-12-13: 100%
| NS | 2025-12-01: 20%; 2025-12-02: 30%; 2025-12-03: 40%; 2025-12-04: 50%; 2025-12-05: 60%; 2025-12-06: 70.3%; 2025-12-08: 80%; 2025-12-09: 85%; 2025-12-10: 90%; 2025-12-11: 95%; 2025-12-12: 100%; 2025-12-13: 100%
Manual Packing - Line 5 | DS | 2025-12-01: FAI; 2025-12-02: 20%; 2025-12-03: 30%; 2025-12-04: 40%; 2025-12-05: 50%; 2025-12-06: 60.3%; 2025-12-08: 70%; 2025-12-09: 80%; 2025-12-10: 85%; 2025-12-11: 90%; 2025-12-12: 95%; 2025-12-13: 100%
| NS | 2025-12-03: 20%; 2025-12-04: 30%; 2025-12-05: 40%; 2025-12-06: 50.25%; 2025-12-08: 60%; 2025-12-09: 70%; 2025-12-10: 80%; 2025-12-11: 85%; 2025-12-12: 90%; 2025-12-13: 95%
| FATP WIP VS Daily demand | [8 empty] | 70.25 | 124.5833 | 2.2355 | 1.6022 | 1.0617 | 0.69289 |  | 0.78635 | 0.87447 | 0.86398 | 0.95666 | 1.0846 | 1.1592 |  | 1.2384 | 1.2678 | 1.2595 | 1.2738 | 1.2864 | 1.2788 |  | 1.264 | 1.2379 | 1.2137 | 1.1822 | 1.1431 | 1.1005
| Forecast-0605 | 2025-11-17: #REF!; 2025-11-24: #REF!; 2025-12-01: #REF!; 2025-12-08: #REF!
| Cum |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Delta(Pack-out vs FCST) | 2025-11-17: #REF!; 2025-11-24: #REF!; 2025-12-01: #REF!; 2025-12-08: #REF!
| CNT capacity | 2025-11-17: #REF!; 2025-11-24: 17692; 2025-12-01: 81662; 2025-12-08: 166816
SMT Learning Curve | bar: 2025-11-09 to 2025-11-18
SMT input |  | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10
Efficiency | Max capacity | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
SMT S2 (6H2G) | 12000 | 1200 | 2400 | 3600 | 4800 | 6000 | 7200 | 8400 | 9600 | 10800 | 12000
SMT S12 (5H2G) | 12000 | 1200 | 2400 | 3600 | 4800 | 6000 | 7200 | 8400 | 9600 | 10800 | 12000
SMT S1 (6H2G) | 12000 | 1200 | 2400 | 3600 | 4800 | 6000 | 7200 | 8400 | 9600 | 10800 | 12000
FATP line Learning Curve (Fungible 1.0 *498)
FATP input |  | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13
Efficiency (Fungible 1.0) |  | 15% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 85% | 90% | 95% | 95% | 95%
Pack-out line-Learning Curve (Pack out UPH 411/manual line, UPH 500/Auto line)
Pack out input |  | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14 | Day15 | Day16
Efficiency - Manual line |  | 15% | 30% | 40% | 50% | 60% | 70% | 80% | 85% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100%
Efficiency - Auto line |  | 3% | 5% | 10% | 20% | 30% | 45% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95% | 95%
Items | Fungible 1.0
UPH/line | 524
Line Qty | 4
Efficiency | 95%
Target Yield Rate | 99.5%
Working hours/Day | 17.75
Working day/Week | 6
DRR | 35167
WRR | 211002
Items | Fungible 1.0
UPH/line | 524
Line Qty | 4
Efficiency | 95%
Target Yield Rate | 99.5%
Working hours/Day | 17.75
Working day/Week | 7
DRR | 35167
WRR | 246169
Note on I5: Author: Cross section and dye & pry: 4pcs Reflow board: 1 panel
Note on T6: Author: Cross section and dye & pry: 4pcs Reflow board: 1 panel
Note on U7: Author: Cross section and dye & pry: 4pcs Reflow board: 1 panel
Note on G14: Trial run before get line qual approval
Note on L16: Trial run before get line qual approval
Note on O16: Include device FAI quantity
Note on O18: Trial run before get line qual approval
Note on S18: Include FAI quantity
Note on S20: Trial run before get line qual approval
Note on V20: Include FAI quantity

## Calypso FCST
FCST version: 20251107153259
Cum FCST | 3441000
Project | PartNumber | SKU | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05
Calypso | 53-100275 | US | 6794 | 0 | 54298 | 116107 | 10656 | 99398 | 49670 | 75832 | 57384 | 53019 | 61186 | 61095 | 79529 | 0 | 0 | 37497 | 70656 | 30588 | 117558 | 38642 | 72626
Calypso | 53-100276 | DE,FR,IT,ES | 0 | 0 | 47168 | 29945 | 122998 | 50428 | 36939 | 55375 | 73486 | 70238 | 64415 | 55041 | 37999 | 0 | 0 | 68122 | 29642 | 17724 | 61195 | 54838 | 74060
Calypso | 53-100763 | AU/NZ | 0 | 67980 | 22530 | 21312 | 55944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calypso | 53-100764 | JP | 2610 | 0 | 16487 | 28203 | 15994 | 22627 | 12180 | 18428 | 17754 | 25186 | 17395 | 25200 | 27039 | 0 | 0 | 95670 | 81273 | 123090 | 30470 | 19108 | 18663
Calypso | 53-100765 | IN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142398 | 17455 | 0 | 26755 | 20749 | 16849 | 20609
Calypso | 53-100766 | BR | 0 | 0 | 0 | 0 | 0 | 17839 | 2670 | 7854 | 2664 | 2034 | 2147 | 4096 | 4099 | 0 | 0 | 2112 | 0 | 35180 | 4126 | 2121 | 13732
Calypso | 53-100767 | MX | 0 | 0 | 4855 | 854 | 3634 | 10753 | 1050 | 46430 | 2664 | 2566 | 4272 | 3424 | 3766 | 0 | 0 | 12552 | 26961 | 8872 | 3902 | 5559 | 4520
Calypso | 53-100769 | ROW-DE | 0 | 0 | 739 | 475 | 523 | 493 | 493 | 537 | 985 | 0 | 0 | 269 | 1956 | 0 | 854 | 856 | 843 | 1095 | 1235 | 802 | 836
Calypso | 53-101569 | CA | 0 | 0 | 10184 | 2880 | 1253 | 9464 | 2499 | 6546 | 3315 | 5209 | 8837 | 9127 | 2676 | 0 | 0 | 11315 | 36794 | 2865 | 6934 | 2749 | 5948
0
| Weekly Cum | (a) | 9404 | 67980 | 156261 | 199776 | 211002 | 211002 | 105501 | 211002 | 158252 | 158252 | 158252 | 158252 | 157064 | 0 | 143252 | 245579 | 246169 | 246169 | 246169 | 140668 | 210994
| Cum |  | 9404 | 77384 | 233645 | 433421 | 644423 | 855425 | 960926 | 1171928 | 1330180 | 1488432 | 1646684 | 1804936 | 1962000 | 1962000 | 2105252 | 2350831 | 2597000 | 2843169 | 3089338 | 3230006 | 3441000
| Internal demand | (b) | 1681
| Trial Run | © | 24 | 24 | 12
|  | Ramp capacity (d) | 11109 | 68871 | 153713 | 208526
|  | Gap (d) - (a+b+c) | 0 | 867 | -2560 | 8750
|  | Cum | 0 | 867 | -1693 | 7057

## CTB status
Calypso CTB summary based on 11/13 ver
Project | Item | LPN | Vendor | Description | PVT Shortage date (on CTB) | CNT comments (PVT material status) | Risk level
Calypso | SMT | 17-004193 | AMPHENOL | ANTENNA,CERAMIC,DK30,SMT-2,(16.2x16.2x4. | 2025-12-12 | Amotech can't be used in DVT, need to ask SAA to pull in, next batch 85k ETA VN 12/18, 100k ETA VN 12/25, will keep tracking with supplier | Middle
Calypso | SMT | 15-001086 | Nexperia | DIODE,TVS,UNI-DIR,CAT-2,H/S,2020Q4,0201( | 2025-12-24 | Nexperia export control, can not support. Need to find 2nd source | Middle
Calypso | SMT | 30-100995 | Meiko/Tripod/VGT | Redesign PCB POR, DVT, Calypso | 2025-11-21 | Typhoon will impact the sea shipping schedule, will arrange air shipment for 28k | Middle
Calypso | SMT | 16-100804 | Linkconn/Fuconn | JDM-CONN,RCPT,USB-C,16P,0.5mm,mid-mount, | 2025-11-21 | 66k is on the way, for the rest of ETA, Fuconn 45k ETA HK 11/18, checking with 2 suppliers about the pull in for the rest of shipment | Middle

## Capacity
Case 1: 6 working days, Max WRR 211,002
VN site | SMT * 3A lines |  |  | FATP * 4A lines | Packing * 5M lines
Items | S1 (B+T) | S2 (B+T) | S12 (B+T) | Fungible 1.0 | Manual line
UPH/line | 600 | 600 | 600 | 524 | 411
Line Qty | 1 | 1 | 1 | 4 | 5
Efficiency | 90% |  |  | 95% | 100%
Yieldrate | 99.5% |  |  | 99.5% | 100%
Working hours/day | 24 |  |  | 17.75 | 17.75
Working days/week | 6 |  |  | 6 | 6
DRR | 12895 | 12895 | 12895 | 35167 | 36476
CUM DRR | 38685 |  |  | 35167 | 36476
WRR | 77370 | 77370 | 77370 | 211002 | 218856
CUM WRR | 232110 |  |  | 211002 | 218856
Case 2: 7 working days, Max WRR 246,169
VN site | SMT * 3A lines |  |  | FATP * 4A lines | Packing * 5M lines
Items | S1 (B+T) | S2 (B+T) | S12 (B+T) | Fungible 1.0 | Manual line
UPH/line | 600 | 600 | 600 | 524 | 411
Line Qty | 1 | 1 | 1 | 4 | 5
Efficiency | 90% |  |  | 95% | 100%
Yieldrate | 99.5% |  |  | 99.5% | 100%
Working hours/day | 24 |  |  | 17.75 | 17.75
Working days/week | 7 |  |  | 7 | 7
DRR | 12895 | 12895 | 12895 | 35167 | 36476
CUM DRR | 38685 |  |  | 35167 | 36476
WRR | 90265 | 90265 | 90265 | 246169 | 255332
CUM WRR | 270795 |  |  | 246169 | 255332

## Tooling status
No. | Site | Part | LPN | Q'ty | WRR/Tool | Cum WRR (6 working days) | Tooling status
1 | VN | Main housing | 20-105049 | 9 | 38016 | 342144 | Divide into 3 batches: * Batch 1 = 3 Main housing (C01/C05/C06) + 3 Lid housing (C01/C06/C08). Copytool qualification on-going. Tooling ready to use date: 11/14 * Batch 2 = 3 Main housing (C03/C04/C07) + 3 Lid housing (C03/C04/C07). Copytool qualification on-going. Tooling ready to use date: 11/20 * Batch 3 = 3 Main housing (C06/C02/C05) + 2 Lid housing (C02/C09). Tooling ready to use date: 11/28 (with lid housing tool C08 which was qualified from Batch 1)
2 |  | Housing lid | 20-105053 | 8 | 40550 | 324400
※ Risk: Batch 1 gap/step result has 1x abnormal, PD/ID checking for data and will review with AMZ ID for specs update
※ Remark:
1. Peak DRR 52,750 ,Peak WRR316,500
2. For Main housing * total 8 sets Copy tools+ 1set Engineering tool, for Housing lid * total 7 sets Copy tools+1 set Engineering tool.
3. Engineering tool need to be replaced with new Cavtiy & Slider by the MP artwork.
※ Capacity by batch:
Batch # | WRR | Part | LPN | Q'ty | WRR/Tool | Cum WRR (6 working days) | Remark
1 | 114048 | Main housing | 20-105049 | 3 | 38016 | 114048
|  | Housing lid | 20-105053 | 3 | 40550 | 121650
2 | 114048 | Main housing | 20-105049 | 3 | 38016 | 114048
|  | Housing lid | 20-105053 | 3 | 40550 | 121650
3 | 81100 | Main housing | 20-105049 | 3 | 38016 | 114048 | Will qualify with 1 lid housing tool which was qualified from Batch 1
|  | Housing lid | 20-105053 | 2 | 40550 | 81100

## Copy tooling schedule
|  | OK2Tool | [5 empty] | 8/1 Get final logo artwork
|  | 2025-06-26 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07
weeks |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Group | Part Name
1 | Engineering tool | Modify Fabrication--Verify two gating solutions simultaneously (Original Engineering tool +one set of copy tool) |  |  |  | T0 | T1 trial | Texture | T2 | TF/FAI/CMK | LBU DVT 4K Molding in LH | Improve cosmetic |  | DVT main build | transfer to VN | Tool trial FAI ,CPK,DVT 1K molding in VN |  | Tool trial change PVT normal logo | Control Run Molding in VN | CNT FATP+HuaNan Measurement+RREL/ Drop & Tumble+Amazon approve |  | Ramp up
2 | Copy Tools: 4 sets Main housing + 4 sets Housing lid | 2025-06-29: Modify Fabrication; 2025-07-27: Waiting for gate verification results; 2025-08-10: Complete the reserved processing+T0; 2025-08-24: T1; 2025-08-31: Wait for the engineering tool improve cosmetic result; 2025-09-14: Texture; 2025-09-21: T2; 2025-09-28: TF,FAI/CMK; 2025-10-05: National Day; 2025-10-12: transfer VN, TF/FAI/CMK; 2025-11-02: Control Run Molding in VN; 2025-11-09: CNT FATP+HuaNan Measurement+RREL/ Drop & Tumble+Amazon approve; 2025-11-23: Ramp up
3 | Copy Tools: 4 sets Main housing + 3 sets Housing lid | 2025-07-06: Modify Fabrication; 2025-08-03: Waiting for gate verification results; 2025-08-17: Complete the reserved processing+T0; 2025-08-31: T1; 2025-09-07: Wait for the engineering tool improve cosmetic result; 2025-09-14: Waiting in line for Texture; 2025-09-21: Texture; 2025-09-28: T2; 2025-10-12: TF,FAI/CMK; 2025-10-19: transfer VN, TF/FAI/CMK; 2025-11-09: Control Run Molding in VN; 2025-11-16: CNT FATP+HuaNan Measurement+RREL/ Drop & Tumble+Amazon approve; 2025-11-30: Ramp up
Remark:
1. Copy tool kick off by 2 group, Main housing 8sets, Housing lid 7sets
2. Group1& Group2 MP in VN,
3. The above Schedule does not include holidays.
4. If there is design modify, the time will be calculated separately.

## BOM Matrix
Project | Region | 53- PN | 52-PN | 31-PN | Remote | Cable | Pallet q'ty | If have FCST | ASIN | UPC | Packout start date | Build qty (from PVT to OK2ship)
Calypso | US | 53-100275 | 52-100667 | 31-101122 | 52-006181 (primary) 52-100494 (alternate) | 55-100633 | 2664 | Y | B0DJGDC3BD | 840414612631 | 2025-11-13 | 125685
| DE-FR-IT-ES-GB-IE | 53-100276 | 52-100667 | 31-101122 | 52-006182 | 55-100633 | 2664 | Y | B0DJGCX6Q2 | 840414634510 | 2025-11-18 | 48508
| AU | 53-100763 | 52-100667 | 31-101122 | 52-006182 | 55-100633 | 2664 | Y | B0DVJ8VJT7 | 840414664043 | 2025-11-20 | 32810
| JP | 53-100764 | 52-100667 | 31-101122 | 52-005905 | 55-100633 | 2628 | Y | B0DVJ64ZLT | 840414695122 | 2025-11-20 | 23713
| IN | 53-100765 | 52-100667 | 31-101122 | 52-100663 | 55-100633 | 2628 | Y | B0DVJF7528 | 840414652538 | 2025-11-19 | 79
| BR | 53-100766 | 52-100667 | 31-101122 | 52-100502 (primary) 52-100617 (alternate) | 55-100633 | 2664 | Y | B0DVK166SV | 840414689107 | 2025-11-21 | 58
| MX | 53-100767 | 52-100667 | 31-101122 | 52-100500 (primary) 52-100615 (alternate) | 55-100633 | 2664 | Y | B0DVJX97PM | 840414612198 | 2025-11-21 | 58
| NL-PL-SE-ROW | 53-100769 | 52-100667 | 31-101122 | 52-100501 (primary) 52-100619 (alternate) | 55-100633 | 2664 | Y | B0DVK2RPFK | 840414684737 | 2025-11-20 | 8
| CA | 53-101569 | 52-100667 | 31-101122 | 52-100498 (primary) 52-100611 (alternate) | 55-100633 | 2664 | Y | B0F7K67DY2 | 840414698758 | 2025-11-21 | 2726

## Pre-seal OBA plan (hidden)
|  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
|  | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15
OBA capacity by Daily | 100% inspection Q`ty | 2025-03-24: 663; 2025-03-26: 663; 2025-03-28: 663; 2025-03-31: 663
| Normal Sampling Q`ty | 3 | 0 | 34 | 51 | 104 | 135 | 0 | 205 | 253 | 337 | 396 | 0 | 455 | 0 | 506 | 548 | 581 | 607 | 624 | 632 | 0 | 640 | 640
| UPH | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Work position | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
| Ramp UP | 0.9 | 0.9 | 0.9 | 0.95 | 0.95 | 0.95 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| work hour | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
| OBA Capa. | 820.8 | 820.8 | 820.8 | 866.4 | 866.4 | 866.4 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912
| Total Q'ty | 666 |  | 697 | 51 | 767 |  | 0 | 868 | 253 | 337 | 396 | 0 |  | 0 | 506 | 548 | 581 | 607 | 624 | 632 | 0 | 640 | 640
OBA capacity by Daily | UPH | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Total Sampling Q`ty | 665.686 | 0 | 700 | 51 | 767 | 135 | 0 | 868 | 253 | 337 | 396 | 0 | 455 | 0 | 506 | 548 | 581 | 607 | 624 | 632 | 0 | 640 | 640
| Work position | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
| work hour per day | 19 |  | 19 | 19 | 19 |  | 19 | 19 | 19 | 19 | 19 | 19 |  | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
| OBA Capa per day. | 821 | 821 | 821 | 867 | 867 | 867 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912
| Gap | 155.314 |  | 121 | 816 | 100 |  | 912 | 44 | 659 | 575 | 516 | 912 |  | 912 | 406 | 364 | 331 | 305 | 288 | 280 | 912 | 272 | 272
| Need time per day | 15.4094 |  | 16.2037 | 1.1184 | 16.8202 |  | 0 | 18.0833 | 5.2708 | 7.0208 | 8.25 | 0 |  | 0 | 10.5417 | 11.4167 | 12.1042 | 12.6458 | 13 | 13.1667 | 0 | 13.3333 | 13.3333

## Internal PO build
[8 empty] | PVT start | [20 empty] | OK2ship
Model | SKU | Internal PO qty |  | Total internal PO qty | Packout date | Ship date |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
|  | Priority-1 | Priority-2/3/4 | Qty |  | Priority-1 | Priority-2/3/4 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11
52- Daily output plan | [7 empty] | 2025-11-17: 691; 2025-11-18: 635; 2025-11-19: 921; 2025-11-20: 2917; 2025-11-21: 3745; 2025-11-22: 4914
53- Daily output plan | [7 empty] | 2025-11-18: 12; 2025-11-19: 760; 2025-11-20: 1850; 2025-11-21: 3328; 2025-11-22: 5135
53-100275 | US | 952 | 502 | 1454 | 11/19 & 20 | 2025-11-21 | 2025-12-09 | 2025-11-19: 339; 2025-11-20: 613; 2025-11-21: ship out; 2025-12-08: 502; 2025-12-09: ship out
53-100276 | DE-FR-IT-ES-GB-IE | 354 | 230 | 584 | 11/18 & 19 | 2025-11-20 | 2025-12-09 | 2025-11-18: 12; 2025-11-19: 342; 2025-11-20: ship out; 2025-12-08: 230; 2025-12-09: ship out
53-100763 | AU | 49 | 17 | 66 | 2025-11-20 | 2025-11-21 | 2025-12-09 | 2025-11-20: 49; 2025-11-21: ship out; 2025-12-08: 17; 2025-12-09: ship out
53-100764 | JP | 61 | 26 | 87 | 2025-11-20 | 2025-11-21 | 2025-12-09 | 2025-11-20: 61; 2025-11-21: ship out; 2025-12-09: 26; 2025-12-10: ship out
53-100765 | IN | 79 | 102 | 181 | 2025-11-19 | 2025-11-20 | 2025-12-09 | 2025-11-19: 79; 2025-11-20: ship out; 2025-12-09: 102; 2025-12-10: ship out
53-100766 | BR | 58 | 8 | 66 | 2025-11-21 | 2025-11-22 | 2025-12-09 | 2025-11-21: 58; 2025-11-22: ship out; 2025-12-09: 8; 2025-12-10: ship out
53-100767 | MX | 58 | 17 | 75 | 2025-11-21 | 2025-11-22 | 2025-12-09 | 2025-11-21: 58; 2025-11-22: ship out; 2025-12-10: 17; 2025-12-11: ship out
53-100769 | DE-NL-PL-SE-ROW | 8 | 11 | 19 | 2025-11-20 | 2025-11-21 | 2025-12-09 | 2025-12-10: 11; 2025-12-11: ship out
53-101569 | CA | 62 | 27 | 89 | 2025-11-21 | 2025-11-22 | 2025-12-09 | 2025-11-21: 62; 2025-11-22: ship out; 2025-12-10: 27; 2025-12-11: ship out
|  | 1681 | 940 | 2621 |  |  |  | 2025-11-18: 12; 2025-11-19: 760; 2025-11-20: 723; 2025-11-21: 178; 2025-11-22: 0
[9 empty] | 0 | 0 | 1127 | 3150 | 5135
Note on D13: Author: Defer this SKU, pending for Packaging update

## Readines checklist
|  | Project | Calypso
SMT line | 3A | Line transfer kick off date | /
FATP line | 4A | LBU build wk | PVT 11/17/2025
Package line | 5M | OK2ship date/Approve date | 12/08/2025
|  | FFS date | 12/10/2025
Category | # | Item | Remark | AMZ DRI | CNT DRI | Status | Due date | Remark
Production line | 1 | Line Set up & Qualification plan | Refer to sheet "Project milestone" & "Line qual summary" | STM Duke Miao/Francis Hu | ME Ryan/Hansen; TE Rain | On-going | 2025-12-01
| 2 | SMT line | Refer to sheet "Project milestone" & "Line qual summary" | STM Francis Hu | ME Hansen | On-going | 2025-11-26
| 3 | FATP line | Refer to sheet "Project milestone" & "Line qual summary" | STM Duke Miao | ME Ryan; TE Rain | On-going | 2025-11-27
| 4 | OBA | Refer to OBA Readiness list | DQM James Hu | PQE a Max/Leon | Close | 2025-11-10
Product identity | 5 | Site Code/Plant code | Site Code: S008538 FULIAN PRECISION TECHNOLOGY LIMITED Lot CN1, Quang Chau Industrial Zone, Nenh Ward, Bac Ninh Province, 22000 |  | PM Ceecee | Close
| 6 | Project name | Keep no change |  | PM Ceecee | Close
| 7 | Product # | Keep no change |  | PM Ceecee | Close
| 8 | BOM | Final BOM need release before PVT start 1 month | NPI PM Luis | PM Ceecee | On-going | 2025-11-14 | BOM list was shared, need Townsend BOM update status to Production before PVT
| 9 | Device code | Device PN: 52-100667. Device code: 42A | NPI PM Luis | PM Ceecee | Close | /
| 10 | SN Rule | Will be ready before PVT | / | PE Sally | Close
| 11 | MAC/Key | Auto MAC/Key will be keep tracking before PVT build 1 wk | NPI PM Luis | PM Ceecee | Close |  | DVT leftover MACs & keys can transfer to PVT
| 12 | Label doc | Label document will be prepared once final BOM released | Package Engineer Do Suh | Package RD Meredith | On-going | 2025-11-15 | Released label document of US & EU, others to be released before 11/15
| 13 | SOP | SOP will be prepared and get approval before PVT start ~1 wk | STM Duke Miao/Francis Hu | IE Lora | Close | 2025-11-14 | SOP was sent to AMZ team on 11/4 - SMT SOP target to get approved by 11/13 - FATP & Packing SOP target 11/14
| 14 | SIP | SIP will be prepared and get approval before PVT start ~1 wk | DQM James Hu | PQE Max/Leon | Close | 2025-11-10
Operation | 15 | FCST | FCST has been released | Planning Tommy Zhou | PM Ceecee | Monitoring | / | Keep tracking with PF update
| 16 | PO Sequence plan | Need AMZ to release PO 6 wks before ok2ship week (2 wks package material preparation+ 0.5 wk IQC trial run checking + 3 wks ramp up production) | Planning Tommy Zhou | PM Ceecee | Monitoring | /
| 17 | ETAC | ETAC running with 53-level BOM from 11/03 | / | PM Ceecee | Close | / | ETAC running every Monday
| 18 | CTB | Keep tracking for PVT |  | MPM April | On-going | Daily
| 19 | FAI build | Based on ramp up plan, refer sheet "Product Milestone" | / | PM Ceecee | Open
| 20 | FAI report | Based on ramp up plan, refer sheet "Product Milestone" | STM Duke Miao/Francis Hu | CFT | Open
| 21 | Ramp up & MP Build plan | Refer to sheet "Ramp up" and "Build plan sheet" | Planning Christy Hu/NPI PM Luis | PM Ceecee | Monitoring | /
| 22 | Shipment plan | Follow PO sequence to arrange | Planning Christy Hu | PM Ceecee | Monitoring | /
| 23 | Pick up plan | FFS date: 12/10, pick up port: B08 1st floor | DGL Rick Pu | PMC Emma | Open | 2025-12-10
| 24 | Export customs documents (packing list and invoice) | Exporter title/address | / | PMC Emma | Open | 2025-12-08
Operation system | 25 | Agile/SAP | Follow BOM list to maintain BOM on system | / | PM Ceecee | Close | /
| 26 | EDI/SFTP | Keep no channel change from AMZ to CNT | / | IT Sunnyone | Close
Control Log | 27 | Control log | OCL, ECL, WCL verification in PVT stage | STM Duke Miao/DQM James Hu | PM Ceecee PQE Leon | On-going | 2025-11-13 | Log files are grabbed from Trial run (11/12 input FATP) ECL document was submitted to AMZ on 11/8
Audit | 28 | QMS audit | Audit items base on AMZ's standard document before trial run. | AMZ team | PQE Max/Leon | On-going | 2025-11-13
Summary:

## Action items
Calypso PVT readiness review action item
No | Item | Contents | CNT DRI | AMZ DRI | Due Date | Status | Remark
3 | Ramp up plan | CNT update ramp up plan which will be add 1 Auto Packing line and reduce 1 manual packing line in ramp period --> Due to abnormal damage during logistics, Auto packing line timeline is extended. Mitigation plan: set up 5th manual packing line for PVT. | PM Ceecee | PM Luis | Weekly | Closed
4 | CET test | CNT update PVT CET test plan --> PVT CET plan was reviewed by DQM | PQE Leon | DQM James | 2025-10-13 | Closed
5 | PVT cost | CNT check and update Total related cost for Calypso PVT --> 1st version quotation sent on 10/17. Need AMZ release PO by 11/17 | BPM Sherine | OPM Luis OPM Teana | 2025-11-17 | On-going
6 | SKUs build start date | CNT update the build start date for each SKUs base on the Internal PO sample demand | CNT PM Alice | PM Luis | 2025-10-02 | Closed | Refer sheet "BOM matrix" and "Internal PO build"
7 | Line qual | AMZ team help review Line qual summary/detail and share comments | ME Ryan & Hansen/ TE Rain | STM Francis/Duke | 2025-10-02 | Closed | Francis request Yank test + side load to qualify HDMI machine 20pcs
8 |  | AMZ team help share FAT trial run quantity for material preparation (AMZ STM Duke) | ME Ryan/ TE Rain | STM Duke | 2025-10-02 | Closed
9 | Shipping paperworks | Work closely on certification tracking for shipments | PMC Emma | DGL & GTC | 2025-11-10 | Closed | Refer to DGL pre-launch sheet
10 | CTB | Update CTB status during PVT to OK2ship | MPM April | MM Tung | Daily | Closed | Refer to CTB status sheet
11 | Rel test | Update Rel test device quantity and release PO --> Rel test request 200pcs, added in Internal demand order |  | PM Luis | 2025-10-31 | Closed
12 | Pre-CET 2 | Update Pre-CET 2 plan --> Loading test done & send report on 11/13. Waiting for AMZ to define the pallet & layout | PQE Leon | DQM James & Packaging team | 2025-11-14 | On-going
13 | CTB | Update supply plan of pallet for PVT packing/storing --> Prioritize using foam pallet for packing & storing while waiting for wooden pallet type finalized | PM Ceecee |  | 2025-11-14 | On-going
14 | SMT 1st date input | SMT line plan: (pending PVT RR green light - expecting at 11/14 09:30 VN time) Line switch: 11/14 06:00 for material preparation FAI start: 11/14 09:30 FAI BOT side ready by 11/14 14:30 FAI Top side ready by 11/14 18:00 FAI testing confirm by 11/14 19:30 SMT complete 204pcs within 11/14 night shift | CNT |  | 2025-11-14 | On-going

## Team roster
Calypso's Amazon Core Team
No | Function | Name | Current DRI's email | Remark
1 | Factory OPM | Tran, Teana | maiteana@amazon.com.vn | Involve PVT phase + MP phase
2 | OPM Manager | Sally, Guo | gjianyin@amazon.com.vn
3 | SMT STM | Francis, Hu | frahusuz@amazon.com | PVT + MP phase
4 | FATP STM | Duke Miao | dukemiao@amazon.com | PVT + MP phase
5 | MM |  |  | MP phase
6 | FMQM | Evan Zhong | xiaoyoz@amazon.com | PVT phase
7 | REL |  |  | MP phase
8 | ORT | Khanh, Luong | lpkhanh@amazon.com.vn | PVT + MP phase
9 | DQM | Hu, James | hushin@amazon.com | PVT phase
10 | SOPM
11 | MPM
Calypso- CNT Team Members
No | Function | Names | Email | Remark | OPM / ME / TE / IE /Quality / MFG
1 | OPM | Ceecee Liang | ceecee.qe.liang@fii-foxconn.com
2 | MPM | April Peng | april.zf.peng@fii-foxconn.com
3 | PC | Shi Miao | shi-miao.chen@fii-foxconn.com
4 | MC | Gina Pei | gina.xj.pei@mail.foxconn.com
5 | PMC | Peter Tang | chun-jing.tang@fii-foxconn.com
6 | BPM | Sherine Ye | sherine.sy.ye@fii-foxconn.com
7 | TPM | Cindy Wang | cindy.wc.wang@fii-foxconn.com
8 | RF (VN) | Justin Wei | justin.dw.wu@fii-foxconn.com
9 | EE (TW) | Ken Huang | kenh.hk.huang@fii-foxconn.com
10 | SW (LH) | Sunny Lu | sunny.gz.lu@fii-foxconn.com
11 | SW (VN) | Nora Ruan | nora.by.ruan@fii-foxconn.com
12 | PD | Randy Bai | randy.wf.bai@fii-foxconn.com
13 | RD Packaging | Meredith Huang | meredith.yx.huang@fii-foxconn.com
14 | ME FATP | John Chen | ru-guang.chen@fii-foxconn.com
15 | ME SMT | Hansen Zheng | hansen.gh.zheng@fii-foxconn.com
16 | ME program | Cinamon Wu | cinamon.sg.wu@fii-foxconn.com
17 | TE | Rain Huang | rain.ww.huang@fii-foxconn.com
18 | PE (FA) | Ryann Ruan | ryann.wx.ruan@fii-foxconn.com
19 | PE (BOM) | Sally Ruan | sally.jc.ruan@fii-foxconn.com
20 | IE | Lora Ruan | lora.st.ruan@fii-foxconn.com
21 | AE | Fisher Zhang | fisher.c.zhang@fii-foxconn.com
22 | PQE | Leon Fan | leon.wl.fan@fii-foxconn.com
23 | SQE | Tong Zhang | tong-zhang.yan@fii-foxconn.com
24 | IQC | Tran Thi Nuong | shi-niang.chen@fii-foxconn.com
25 | SMT | Nguyen Van Cuong | csd-vn-smt@mail.foxconn.com
26 | HDMI | Nguyen Kha Son | csd-vn-smt@mail.foxconn.com
27 | SI | Le Van Thuy | csd-vn-si@mail.foxconn.com
28 | Kitting SMT | Nguyen Thi Thom | cbd-vn-kitting@mail.foxconn.com
29 | Kitting SI | Nguyen Van Huy | cbd-vn-kittingb08-3f@fii-foxconn.com
30 | REL | Tonny Pan | tonny.dy.pan@fii-foxconn.com
31 | IT SF | Ly Van Hop | vngz-cbd-sfc@fii-foxconn.com
32 | Security | Daisy Ruan | daisy.sh.nguyen@fii-foxconn.com